## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2171-swen-261-08-C
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing
*SPRINT 1* | Acceptance Criteria
Story (Player Sign-in) | **Given** that I have not signed in **when** I see the Home page **then** I must see a means to sign-in. (such as a link or button) **Given** that I am not signed-in **when** I do click on the sign-in link **then** I expect to be taken to the Signin page, with a means to enter a player name. **Given** that no one else is using my name **when** I enter my name containing only alphanumeric characters or spaces in the sign-in form and click the **Sign-in** button **then** I expect the system to reserve my name and navigate back to the Home page. **Given** that I am on the Signin page **when** I enter a name that contains one or more characters that are not alphanumeric or spaces and click the **Sign-in** button **then** I expect the system to reject this name and return the Signin form. **Given** that someone else with my name has signed-in **when** I enter my name in the Signin form **then** I expect the system to reject my sign-in and return the Signin form for me to try another name. **Given** that I am signed-in **when** I navigate to the Home page **then** I expect to see a list of all other signed-in players. (_NOTE_: in the next story you will use this list to pick opponents for checkers games.) **Given** that I am _not_ signed-in **when** I navigate to the Home page **then** I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Testing Passed -IF Regression testing passed 4/1/2018 -LD
*SPRINT 2* | Acceptance Criteria
Story (Start a Game) | **Given** that I'm signed in **when** I view the Home page **then** I can start a game by selecting a player listed on the Home page. **Given** that the player I selected isn't yet in a game **when** I select that player **then** the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. **Given** that the player I selected is already in a game **when** I select that player **then** the system will return me to the Home page with an error message. **Given** that I'm waiting for a game **when** another player selects a game with me **then** the system will automatically send me to the _Game View_ from the Home page. _NOTE_: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. **Given** a valid, initial game board **when** I drag a piece to a white space **then** the piece should **not** be _droppable_. **Given** a valid, initial game board **when** I drag a piece to an occupied space **then** the piece should **not** be _droppable_. **Given** a valid, initial game board **when** I drag a piece to an open space **then** the piece should be _droppable_. _NOTE_: In this Story the drop action should not do anything; piece movement validation will be the focus of future stories. **Given** a valid, initial game board **when** I view the board in the browser **then** my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Testing passed, all acceptance criteria functional -IF
Story (Player Sign Out) | **Given** that I am in a game **when** I hit the sign out button **then** I want to forfeit the game and be logged out. **Given** that I am in the player lobby **when** I sign out **then** I want to be removed from the player lobby and logged out. | Testing passed, all acceptance criteria functional 3/28/18 -AH
Story (Single Move) | **Given** that it is my turn **when** I drag a piece diagonally forward from my piece's current location to move **then** I expect my piece to move. **Given** that it is my turn **when** I drag my piece onto a space already occupied **then** I expect to be returned to my original place with an error. **Given** that I attempt to move laterally or backwards **when** I move my piece **then** I expect to be returned to my original place with an error. **Given** that I try to move to a white space **when** I drag my piece **then** I expect to be returned to my original place with an error. **Given** that I attempt to move to a space not adjacent to my piece's current location **when** I move my piece **then** I expect to be returned to my original place with an error. _NOTE:_ This does not apply in the case of a jump move. **Given** that its not my turn **when** I try to move **then** I expect to not be able to. **Given** that I am finished with my turn **when** I click Submit Turn **then** I expect my turn to be completed and for it to become my opponent's turn. | Testing passed, all acceptance criteria functional -IF
Story (Resignation) | **Given** that I wish to leave the game **when** I press the resign button **then** I expect to lose the game and be returned to the Player Lobby. **Given** that my partner resigns **when** we are in a game, **then** I expect to win the game and be returned to the Player Lobby. | Testing pushed to Sprint 3
Story (Single Jump Move) | **Given** that it is my turn **when** there is an opponent's piece in my path with an empty space beyond it, **then** I expect to jump over the opponent piece and capture it. **Given** that there are other move options besides a jump move **when** I take my turn **then** I expect to be forced to make the jump move. **Given** that there are multiple single-jump move options **when** it is my turn **then** I expect to be able to choose my move between these jump options. **Given** that I jump an opponent's piece **when** it is my turn **then** I expect to capture that piece (the piece to be removed from the board). **Given** that the space beyond the opponent's piece is not empty **when** I attempt to jump their piece **then** I expect to be returned to my original position with an error message. | Testing pushed to Sprint 3
Story (Multi Jump Move) | **Given** that there are multiple opponent's pieces in my path with connecting empty spaces behind them **when** I attempt to move my piece **then** I expect to jump over multiple pieces and capture them. **Given** that I single-jump over one opponent's piece **when** there are more jumpable opponent's pieces from my current position, **then** I expect to have to jump over those pieces as well. **Given** that there are multiple multi-jump options available **when** it comes time to take my turn **then** I expect to be able to choose one. | Testing pushed to Sprint 3

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button)
Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name.
Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page.
Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.)
Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name.
Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all.
Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page.
Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.)
Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons).
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message.
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories.
Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world.