## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2171-swen-261-08-C
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing
*SPRINT 1* | Acceptance Criteria
Story (Player Sign-in) | Given that I have not signed in when I see the Home page then I must see a means to sign-in. (such as a link or button)
Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name.
Given that no one else is using my name when I enter my name containing only alphanumeric characters or spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page.
Given that I am on the Signin page when I enter a name that contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Signin form.
Given that someone else with my name has signed-in when I enter my name in the Signin form then I expect the system to reject my sign-in and return the Signin form for me to try another name.
Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.)
Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons).
*SPRINT 2* | Acceptance Criteria
Story (Start a Game) | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message.
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the home.ftl HTML includes a <meta> tag that tells the browser to refresh the game every 5 seconds; thus you need to update the GetHomeRoute controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement validation will be the focus of future stories.
Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world.
Story (Player Sign Out) | Given that I am in a game when I hit the sign out button then I want to forfeit the game and be logged out.
Given that I am in the player lobby when I sign out then I want to be removed from the player lobby and logged out.
Story (Single Move) | Given that it is my turn when I drag a piece diagonally forward from my piece's current location to move then I expect my piece to move.
Given that it is my turn when I drag my piece onto a space already occupied then I expect to be returned to my original place with an error.
Given that I attempt to move laterally or backwards when I move my piece then I expect to be returned to my original place with an error.
Given that I try to move to a white space when I drag my piece then I expect to be returned to my original place with an error.
Given that I attempt to move to a space not adjacent to my piece's current location when I move my piece then I expect to be returned to my original place with an error. NOTE: This does not apply in the case of a jump move.
Given that its not my turn when I try to move then I expect to not be able to.
Given that I am finished with my turn when I click Submit Turn then I expect my turn to be completed and for it to become my opponent's turn.
*SPRINT 3* | Acceptance Criteria
Story (Resignation) | Given that I wish to leave the game when I press the resign button then I expect to lose the game and be returned to the Player Lobby.
Given that my partner resigns when we are in a game, then I expect to win the game and be returned to the Player Lobby.
Epic (Jump Moves)
Story (Single Jump Move) | Given that it is my turn when there is an opponent's piece in my path with an empty space beyond it, then I expect to jump over the opponent piece and capture it.
Given that there are other move options besides a jump move when I take my turn then I expect to be forced to make the jump move.
Given that there are multiple single-jump move options when it is my turn then I expect to be able to choose my move between these jump options.
Given that I jump an opponent's piece when it is my turn then I expect to capture that piece (the piece to be removed from the board).
Given that the space beyond the opponent's piece is not empty when I attempt to jump their piece then I expect to be returned to my original position with an error message.
Story (Multi Jump Move) | Given that there are multiple opponent's pieces in my path with connecting empty spaces behind them when I attempt to move my piece then I expect to jump over multiple pieces and capture them.
Given that I single-jump over one opponent's piece when there are more jumpable opponent's pieces from my current position, then I expect to have to jump over those pieces as well.
Given that there are multiple multi-jump options available when it comes time to take my turn then I expect to be able to choose one.
Story (King Me) | Given that my piece is not a king when it reaches the opponent's end of the board, then I expect it to be kinged.
Story (Winning) | Given that I have captured the last of my opponent's pieces when I execute my turn then I expect to have won the game.
Given that my opponent resigns when it becomes my turn then I expect to have won the game.
Given that my opponent is out of moves when it becomes my turn then I expect to have won the game.
Story (Getting Help) | Given that I need help when I click the Help button then I expect my valid moves to be shown on the board.
Epic (Tournament Mode)
Story (Tournament Scoreboard) | Given that I am a player when I sign in then I expect an option to sign in as a tournament player.
Given that I want to view the tournament standings, when I click the View Scoreboard link then I expect to be redirected to a page with the standings of current, signed-in tournament mode players.
Story (Recording a Tournament Game Result) | Given that I have just won a game when I click a link to view the scoreboard then I expect to see my new ranking.

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | Testing Passed (IF) Regression testing passed 4/1/2018 (LD)
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | Testing passed, all acceptance criteria functional (IF)
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | Testing passed, all acceptance criteria functional (IF)
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | Testing passed, all acceptance criteria functional (IF)
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | Testing passed, all acceptance criteria functional (IF)
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | Testing passed, all acceptance criteria functional (IF)
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | Testing passed, all acceptance criteria functional (IF)
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | Testing passed, all acceptance criteria functional (IF)
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | Testing passed, all acceptance criteria functional (IF)
As a player who is signed into WebCheckers I want to sign out so that I am not placed in any new games. | Given that I am in a game when I hit the sign out button then I want to forfeit the game and be logged out. |  |  |  | Testing passed, all acceptance criteria functional 3/28/18 -AH
| Given that I am in the player lobby when I sign out then I want to be removed from the player lobby and logged out. |  |  |  | Testing passed, all acceptance criteria functional 3/28/18 -AH
As a Player I want to move a piece diagonally away from me so that I can advance to towards the far end of the board. | Given that it is my turn when I drag a piece diagonally forward from my piece's current location to move then I expect my piece to move. |  |  |  | Testing passed, all acceptance criteria functional -IF
| Given that it is my turn when I drag my piece onto a space already occupied then I expect to be returned to my original place with an error. |  |  |  | Testing passed, all acceptance criteria functional -IF
| Given that I attempt to move laterally or backwards when I move my piece then I expect to be returned to my original place with an error. |  |  |  | Testing passed, all acceptance criteria functional -IF
| Given that I try to move to a white space when I drag my piece then I expect to be returned to my original place with an error. |  |  |  | Testing passed, all acceptance criteria functional -IF
| Given that I attempt to move to a space not adjacent to my piece's current location when I move my piece then I expect to be returned to my original place with an error. NOTE: This does not apply in the case of a jump move. |  |  |  | Testing passed, all acceptance criteria functional -IF
| Given that its not my turn when I try to move then I expect to not be able to. |  |  |  | Testing passed, all acceptance criteria functional -IF
| Given that I am finished with my turn when I click Submit Turn then I expect my turn to be completed and for it to become my opponent's turn. |  |  |  | Testing passed, all acceptance criteria functional -IF
As a player who is in an ongoing game I want to be able to forfeit the game so that I can return to the lobby. | Given that I wish to leave the game when I press the resign button then I expect to lose the game and be returned to the Player Lobby. |  |  |  |  | Failed, bug during rerouting 4/16/2018 (LD)
| Given that my partner resigns when we are in a game, then I expect to win the game and be returned to the Player Lobby. |  |  |  |  | Failed, bug during rerouting 4/16/2018 (LD)
As a Player, I want to be able to jump diagonally forward with a single piece or in either direction with a King over an opponent piece so that I can eliminate their piece and advance in the game. | Given that it is my turn when there is an opponent's piece in my path with an empty space beyond it, then I expect to jump over the opponent piece and capture it. |  |  |  |  | Passed 4/16/2018 (LD)
| Given that there are other move options besides a jump move when I take my turn then I expect to be forced to make the jump move. |  |  |  |  | Passed 4/16/2018 (LD)
| Given that there are multiple single-jump move options when it is my turn then I expect to be able to choose my move between these jump options. |  |  |  |  | Passed 4/16/2018 (LD)
| Given that I jump an opponent's piece when it is my turn then I expect to capture that piece (the piece to be removed from the board). |  |  |  |  | Passed 4/16/2018 (LD)
| Given that the space beyond the opponent's piece is not empty when I attempt to jump their piece then I expect to be returned to my original position with an error message. |  |  |  |  | Passed 4/16/2018 (LD)
As a Player I want to be able to diagonally jump over several of my opponents pieces in one turn so that I can eliminate two or more of their pieces. | Given that there are multiple opponent's pieces in my path with connecting empty spaces behind them when I attempt to move my piece then I expect to jump over multiple pieces and capture them. |  |  |  |  | Passed 4/17/2018 (LD)
| Given that I single-jump over one opponent's piece when there are more jumpable opponent's pieces from my current position, then I expect to have to jump over those pieces as well. |  |  |  |  | Passed 4/17/2018 (LD)
| Given that there are multiple multi-jump options available when it comes time to take my turn then I expect to be able to choose one. |  |  |  |  | Passed 4/17/2018 (LD)
As a Player I want to have my piece become a King so that I can move diagonally forward and backwards. | Given that my piece is not a king when it reaches the opponent's end of the board, then I expect it to be kinged.
As a Player, I want to win the game by capturing all of my opponent pieces so that I can claim victory. | Given that I have captured the last of my opponent's pieces when I execute my turn then I expect to have won the game.
Given that my opponent resigns when it becomes my turn then I expect to have won the game.
Given that my opponent is out of moves when it becomes my turn then I expect to have won the game.
As a Player, I want to have valid next-moves shown to me when I request help so that I can advance in the game. | Given that I need help when I click the Help button then I expect my valid moves to be shown on the board.
As a competitive player interested in tournament rankings I want to be able to view the tournament ladder so that I can follow the tournament. | Given that I am a player when I sign in then I expect an option to sign in as a tournament player.
Given that I want to view the tournament standings, when I click the View Scoreboard link then I expect to be redirected to a page with the standings of current, signed-in tournament mode players.
As a Player I want to see the tournament scoreboard so that I know my standing. | Given that I have just won a game when I click a link to view the scoreboard then I expect to see my new ranking.